## Instructions
PRJ 00000 PM2 Proposal Project Budget | INSTRUCTIONS are below
The Project Budget Template includes sample data for illustration purposes, which will need to be amended to reflect your specific situation.
Review, amend, add to or delete the descriptions of expenditures, as required, to tailor to your specific situation. Then input your cost ($USD) and unit estimates.
All calculated figures are in colored in orange, to assist easy recognition, however, the color may be changed as desired. The worksheet uses simple Excel calculations which may be altered as required. After changes have been made to the worksheet, it is recommended that the calculations are checked.
Software System Selection
Risk Evaluation and Mititgation
www.axia-consulting.co.uk

## Project Budget Template
| Year, Quarter, or month (depending on plan): |  |  | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3
|  |  | Rate $ per | Quantity |  | Quantity |  | Quantity |  | Quantity
|  | Expenditure Type | Unit/Day | Units/Days |  | Units/Days |  | Units/Days |  | Units/Days |  | Total
Ref | Project Expenditures | (Capital/ Expense) |  |  | $ |  | $ |  | $ |  | $ | $
1 | Proposal Phase Costs
1.1 | Internal resources / staff costs: ($100 USD per hour)
1.1.1 | - Information Systems (IS) department |  | 100 | 400 | 40000 | 400 | 40000 |  | 0 |  | 0 | 80000
1.1.2 | - user departments |  | 100 | 40 | 4000 | 40 | 4000 |  | 0 |  | 0 | 8000
1.1.3 | - procurement department |  | 100 | 8 | 800 | 8 | 800 |  | 0 |  | 0 | 1600
1.1.4 | - add other internal resources as required |  | 100 |  | 0 |  | 0 |  | 0 |  | 0 | 0
1.2 | Travel and expenses |  | n/a | [8 empty] | 0
1.3 | Specification / RFP tools and programs |  | n/a | [8 empty] | 0
1.4 | Consultancy assistance |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
1.5 | Legal assistance |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
| Total Planning Phase costs |  |  |  | 44800 |  | 44800 |  | 0 |  | 0 | 89600
Project Budget - Execution through Close
2 | Software costs
2.1 | Application software user licences |  | 750 | 0 | 0 | 20 | 15000 | 20 | 15000 | 20 | 15000 | 45000
2.2 | Software as a Service costs |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0
2.3 | Software modifications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Additional licences eg Citrix, EDI software |  | 50 | 0 | 0 | 10 | 500 | 0 | 0 | 0 | 0 | 500
2.5 | Database user licences |  | 200 | 0 | 0 | 2 | 400 | 0 | 0 | 0 | 0 | 400
2.6 | Operating system |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7 | Additional security applications |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 15900 |  | 15000 |  | 15000 | 45900
3 | Hardware costs
3.1 | Servers (new or upgraded, dedicated or shared) |  | 20000 | 0 | 0 | 2 | 40000 | 0 | 0 | 0 | 0 | 40000
3.2 | PC's (new or upgrades) |  | 1000 | 0 | 0 | 25 | 25000 | 0 | 0 | 0 | 0 | 25000
3.3 | Additional memory |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Additional cpu |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | Additional processing services (temporary or permanent) eg via cloud services or other internal resource |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | Printers |  | 1000 | 0 | 0 | 5 | 5000 | 0 | 0 | 0 | 0 | 5000
3.7 | Scanners |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.8 | UPS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9 | Back up devices |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Disk storage |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 70000 |  | 0 |  | 0 | 70000
4 | Network costs
4.1 | Cabling or wireless LAN, WAN or other network |  | 5000 | 0 | 0 | 1 | 5000 | 0 | 0 | 0 | 0 | 5000
4.2 | Racks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Routers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Switching devices |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.5 | Modems |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.6 | Leased or dedicated lines |  | 5000 | 0 | 0 | 1 | 5000 | 0 | 0 | 0 | 0 | 5000
4.7 | Communications software |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.8 | Internet access eg ADSL / broadband, satellite |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 10000 |  | 0 |  | 0 | 10000
5 | Labor costs
For implementation tasks eg: system installation, integration, tailoring, interface development, process re-engineering, report writing, functional and user testing, data conversion and documentation
5.1 | Project team
5.1.1 | Project manager |  | 100 | 0 | 0 | 10 | 1000 | 10 | 1000 | 0 | 0 | 2000
5.1.2 | Project leader |  | 100 | 0 | 0 | 20 | 2000 | 20 | 2000 | 0 | 0 | 4000
5.1.3 | Systems analysts |  | 100 | 0 | 0 | 10 | 1000 | 0 | 0 | 0 | 0 | 1000
5.1.4 | Programmers |  | 100 | 0 | 0 | 20 | 2000 | 20 | 2000 | 0 | 0 | 4000
5.1.5 | Systems testers |  | 100 | 0 | 0 | 20 | 2000 | 30 | 3000 | 0 | 0 | 5000
5.1.6 | Vendor consultants |  |  | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0
5.1.7 | Additional team resources eg contractors, temporary staff, other consultants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1.8 | Travel and expenses |  | n/a | [8 empty] | 0
| Sub total |  |  |  | 0 |  | 8000 |  | 8000 |  | 0 | 16000
5.2 | Business Team
5.2.1 | Business team leader |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.2 | Business team members |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2.3 | Business team managers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
5.3 | Support Team
5.3.1 | Client manager |  | 100 | 0 | 0 | 4 | 400 | 4 | 400 | 0 | 0 | 800
5.3.2 | IS support |  | 100 | 0 | 0 | 6 | 600 | 6 | 600 | 0 | 0 | 1200
5.3.3 | DB analyst |  | 100 | 0 | 0 | 2 | 200 | 2 | 200 | 0 | 0 | 400
5.3.4 | Networking support |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 1200 |  | 1200 |  | 0 | 2400
5.4 | Project team and office costs
5.4.1 | Temporary office accommodation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.2 | Furniture, stationery and supplies |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.3 | Additional telephones and lines |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.4 | Project tools eg project management software, testing programs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.5 | Project website set up and maintenance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.6 | Administrative support |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.7 | Communications costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.8 | Video teleconferencing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.9 | Printing eg user manuals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.10 | Project information / education / marketing materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.11 | Project team or user recognition / awards |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
6 | Training
6.1 | Technical training for implementation team (by vendor) |  | 2500 | 0 | 0 | 10 | 25000 | 0 | 0 | 0 | 0 | 25000
6.2 | Training key users (by vendor) |  | 2500 | 0 | 0 | 4 | 10000 | 10 | 25000 | 0 | 0 | 35000
6.3 | Temporary training facilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 | Training remainder of users (internally or by vendor) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5 | Training materials |  | n/a |  | 5000 | [6 empty] | 5000
6.6 | Travel and expenses to attend training |  | n/a | [8 empty] | 0
| Sub total |  |  |  | 5000 |  | 35000 |  | 25000 |  | 0 | 65000
7 | Data costs
7.1 | Data clean up / de-duplication |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2 | Data archiving |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
8 | Other costs
8.1 | Quality assurance |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.2 | Internal audit review(s) of new system(s) |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.3 | Project steering group |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.4 | Decommissioning of legacy systems |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.5 | Networking with other organisations, who are using / implementing the same system(s) - travel and expenses costs |  | n/a | [8 empty] | 0
8.6 | Attending conferences, software vendor user groups, networking, meetings - fees, travel and expenses costs |  | n/a | [8 empty] | 0
| Sub total |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
9 | Overheads
9.1 | Additional heat, air conditioning, light, power for project implementation and ongoing live running (leasing) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.2 | JCI allocated business costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub total |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0
10 | Contingency
10.1 | Estimated 10% of total project costs |  |  |  | 0 |  | 20000 |  | 10000 |  | 0 | 30000
| Total implementation costs |  |  |  | 5000 |  | 160100 |  | 59200 |  | 15000 | 239300
11 | Ongoing costs
11.1 | Annual vendor maintenance / service charges for:
11.1.1 | - software |  | 14000 | 0 | 0 | 0 | 0 | 1 | 14000 | 1 | 14000 | 28000
11.1.2 | - hardware |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.1.3 | - database |  | 1000 | 0 | 0 | 0 | 0 | 1 | 1000 | 1 | 1000 | 2000
11.2 | Internal IS support |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11.3 | Disaster recovery for systems and data (internally or outsource to remote location) |  | 1000 | 0 | 0 | 5 | 5000 | 2 | 2000 | 2 | 2000 | 9000
| Total ongoing costs |  |  |  | 0 |  | 5000 |  | 17000 |  | 17000 | 39000
Project cost calculations
| Total project cost | [10 empty] | 367900